## checklist
CHECKLIST |  |  |  | TOEIC TEST WEBSITE
Project Start | 2018-12-11 |  |  |  |  | Project End | 2018-12-24
TASK | OWNER | PRIORITY | START | END | % COMPLETE | DONE | NOTES
Requirements | [5 empty] | 0
Introduction | Lê Trung Đức | LOW | 2018-12-11 | 2018-12-12 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Overall Description | Võ Anh Nguyên | MEDIUM | 2018-12-12 | 2018-12-14 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
External Interface Requirements | Mạc Cự Đăng Khoa | HIGH | 2018-12-14 | 2018-12-16 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
System Features | Bùi Huỳnh Hạo Thiên | HIGH | 2018-12-14 | 2018-12-16 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Other nonfunctional requirements and other requirements | All team | MEDIUM | 2018-12-14 | 2018-12-16 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Review and call to fix | Đào Anh Huy | MEDIUM | 2018-12-16 | 2018-12-18 | 100% | 0 | Deliver the product according to the intended time and try to correct it when requested by the customer.
Design | [5 empty] | 0
Login and registration | Mạc Cự Đăng Khoa | LOW | 2018-12-16 | 2018-12-18 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting The interface exactly matches the requirements set. Some parts need correcting
Main screen | Mạc Cự Đăng Khoa | HIGH | 2018-12-16 | 2018-12-18 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Detail screen | Mạc Cự Đăng Khoa | HIGH | 2018-12-16 | 2018-12-18 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
UML Diagram | Võ Anh Nguyên | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
UML Diagram | Lê Trung Đức | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
| Bùi Huỳnh Hạo Thiên | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
| Đào Anh Huy | HIGH | 2018-12-16 | 2018-12-19 | 100% | 0 | The interface exactly matches the requirements set. Some parts need correcting
Code - Front end | [5 empty] | 0
Registration | Mạc Cự Đăng Khoa | MEDIUM | 2018-12-18 | 2018-12-20 | 100% | 0
Home screen | Mạc Cự Đăng Khoa | HIGH | 2018-12-18 | 2018-12-20 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Detail screen | Mạc Cự Đăng Khoa | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Đào Anh Huy | HIGH |  |  | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Bùi Huỳnh Hạo Thiên | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Lê Trung Đức | HIGH |  |  | 100% | 0 | Code clean, easy to understand but there are some missing functions.
| Võ Anh Nguyên | HIGH | 2018-12-19 | 2018-12-21 | 100% | 0 | Code clean, easy to understand but there are some missing functions.
Code - Back end | [5 empty] | 0 | Code clean, easy to understand but there are some missing functions.
Login and registration | Võ Anh Nguyên | MEDIUM | 2018-12-21 | 2018-12-22 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Exams | Bùi Huỳnh Hạo Thiên | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Đào Anh Huy | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Mạc Cự Đăng Khoa | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
| Lê Trung Đức | MEDIUM | 2018-12-20 | 2018-12-23 | 100% | 0 | Relatively complete and detailed database. deliver the product on time but there are some functions of the web that are incomplete
Unit Testing | [5 empty] | 0
Re-check customer requirements | All team | HIGH | 2018-12-24 | 2018-12-27 | 100% | 0
Check requirements | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 100% | 0
Check front end | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 90% | 0
Check back end | All team | MEDIUM | 2018-12-24 | 2018-12-27 | 90% | 0